## Slide 1: Worcester Memorial Marketplace Proposal The revitalization of Worcester Memorial Auditorium
Worcester Contracting
Vandana Anand, Jody Carregal, Kaidi Ding,
David Hinckley Jr., Somesh Patel and Allison Sichler
August 9, 2020
Group 8
Notes: Hi everyone! We will be focusing on the city of Worcester located in MA today and wanted to share some facts pertaining to our project, did you know that Worcester is home to 184,000 people? Or that it is has 9 colleges with over 34,000 students total? Worcester has a rich diversity and we plan to take advantage of that fact. This is what we will be presenting to you today.
My name is Vandana, [go over everyone’s names], and we are the General Contracting team called Worcester proposing the revitalization of the Worcester Memorial Museum into a Marketplace to you, the City of Worcester council members and other investors. Not only would it be a hotspot for entertainment for students, tourists, or locals, but it would also give the opportunity to entrepreneurs looking to expand their businesses or give back to the community. We want to transform this area into a place everyone would be able to enjoy.
Who are we (subject matter experts) and who is our audience (city council, whoever is funding this idea)?
Summary of project, why does it matter, how will it have an impact financially, socially, or structurally
Have a business case and justify the project’s existence

## Slide 2: Agenda
Introduction
Background
Goal
Floor Plans
Associated Risks
Financials
Timeline
Responsibilities
Levels of Effort
Conclusion

## Slide 3: We aim to commercialize the Worcester Memorial Auditorium to maximize the memorials potential economic impact
Notes: We aim to commercialize the Worcester Memorial Auditorium to maximize the memorials economic impact. The memorial officially shut its doors in 2007 and has since sat in one of the most popular intersections in the city of Worcester deemed ‘useless’. We plan to alter this outlook - and make the auditorium a popular site for the citizens of Worcester to visit. The memorial will become a marketplace open for entrepreneurs in the area to sell their products and food, for a night out in the city on a restaurant patio, or for an event hosted in what was the little theatre. The goal is for this site to be one of the most beneficial revitalization projects the city of Worcester has seen in a long time.

## Slide 4: Our Vision
Notes: Selling this project to a group prepared to take on the responsibility of finding vendors and completing the interior design of the memorial will allow this project to blossom. With our provided blueprints and vision this project can only prosper and foster an environment for entrepreneurs to break ground. Not to mention - the fine dining and marketplace hustle and bustle will attract the many college students residing in the city of Worcester
→ Photo citation: Copyright 2019 Walter M. Henritze - All Rights Reserved

## Slide 5: Worcester Memorial Auditorium
Revealed on September 26th, 1933
110,668 square feet
2.43 acres
Officially closed in 2007
Notes: The Worcester Memorial Auditorium design was influenced by Classical Revival with large Doric columns on the front facade with a strong Art Deco influence both inside and out. The auditorium consists of 110,668 square feet on 2.42 acres at Lincoln Square, off the north end of Main Street. The completed product was revealed in 1933 on September 26th at 8:00P.M with a week long celebration which began with concerts and special programs. Since the auditorium's completion the building has been utilized as an entertainment and sports venue hosting musical performances, NCAA basketball games, and graduation ceremonies among many other events.
Citation: Kotsopoulos, N. (2019, May 24). Worcester agrees to sell Worcester Memorial Auditorium to Architectural Heritage Foundation. Retrieved August 02, 2020, from https://www.telegram.com/news/20190523/worcester-agrees-to-sell-worcester-memorial-auditorium-to-architectural-heritage-foundation

## Slide 6: Game Plan From Theatre to.. ..A Multipurpose Entertainment Space Worcester Memorial Auditorium Worcester Memorial Marketplace
A memorial for War heros and a stage for performances, shows and basketball games
A shopping/dining experience with a reflection of the history of the city as well as a flare of the modern revolution that has begun taking over the city.

## Slide 7: 01. Basement Conversion 02. First Floor Marketplace 03. Second Floor Marketplace 04. Third Floor & Patio 05. Little Theatre The Transformation
Converting the basement to a parking garage because the site does not have parking
Existing main stage and theatre will be transformed into a new marketplace for retail style vendors
Additional marketplace area predominantly for food related vendors
Newly built floor will house two fine dining restaurants with the option of indoor or outdoor dining
Multipurpose entertainment area

## Slide 8: Basement Floor Plan
Notes: Blueprint of the basement. The Original basement area was used for deliveries, storage and extra space. The Worcester Memorial Marketplace will have parking in the basement because of the sites lack of parking. They will enter on one side and have one way roads to exist on the other side. Spaces include compact, traditional and handicap spots. This will help the parking situation, but customers will likely need to walk or park in nearby lots.

## Slide 9: First Floor Plan
Notes: The main floor area consisted of the main stage, auditorium seating, and the basement are of the Little Theater. The first floor now becomes the main marketplace with vendor stalls, small stores and some seating areas.

## Slide 10: Second Floor Plan
Notes: The former balcony area now becomes a marketplace with seating and vendor spaces. The marketplace on this floor is for local food, cookware and premade food vendor's. On the left side the little theater has an open space below the seating as well as a stage. The theater will be used as a multipurpose entertainment space.

## Slide 11: Third Floor Plan
Notes: What was once just the top of the second floor balcony, now became a full floor used for fine dining. The now third floor has the ability to have 2 restaurants both with indoor and outdoor dining, each with their own kitchen. On the left side the little theater has a bar and a dj booth on the top floor with terraced seating going down towards the stage.

## Slide 12: Technical Risks Asbestos Lead Paint Old Wiring Structural Damage Water Damage
Highly toxic material used in construction
Toxic paint additive now banned
Ageing wiring can cause fires or burns
Can increase schedule and cost in event of collapse
Can cause mold, decay, and structural damage
Notes: Next we will look at some of the risks associated with this project. There are two main categories of risk: technical and external. First, we will look at the technical risks we might encounter and some strategies to mitigate their impact on the project. Most of the technical risks stem from the fact that this is an old building which has been vacant for several years. It was built in a time where certain toxic materials which are now not used were common building materials. This includes asbestos and lead paint. Asbestos can be found in many different building materials including insulation, tiling, and adhesives. If found, the area must be sealed off and specialists brought in to remove it. Lead paint was a common paint additive before in was banned in the US in 1977, so any paint before this date most likely contains lead. It is often painted over but poses a risk if a wall is drilled into and particles are allowed to get into the air. As in the case of asbestos, the area will have to be sealed off and the paint removed if found. Due to the age of the building and lack of upkeep, there is also a high probability of finding old wiring, structural damage, and water damage. Faulty or ageing wiring could shock and burn workers or worst case scenario cause an electrical fire. Water damage could cause mold and decay in the building, leading to an unhygienic workplace. It has the potential to cause structural damage if left for long periods of time. Structural damage may also be present due to the age of the building. Structural instability or even collapse could increase time and money needed to renovate the building. All of these risks pose a safety threat to the workers on this site as well as a threat to the triple constraint. Finding something like asbestos or lead paint halfway through the project will cause construction to halt until it has been properly removed. Removal is expensive as well, so it could greatly increase cost. There are several ways to mitigate the dangers these risks pose to the project. Careful planning in the design and planning phase will reduce the impact of these risks. A thorough inspection of the building could help to identify any toxic materials, old wiring, or damage to the building present so we will not be surprised by them later on. If identified in the beginning, they can be worked into the baseline schedule and cost ensuring we finish the project on time and in budget. In addition, some extra funds may be put aside in case any of these risks are identified later in the project.

## Slide 13: External Risks Traffic Pests Historical Preservation Economic Recession
Can carry diseases and chew wires
Can cause delays in schedule
Must be careful to preserve historical significance
Could affect selling price and material costs
Notes: Now we will look at some of the external risks associated with the project. The first external risk is traffic. The Worcester Aud is located near several major, busy streets. High traffic may cause delays in our schedule. In addition, construction at the site may cause delays to traffic when we are performing work outside. The best way to mitigate this risk is to plan for it. We will work with the Worcester Police Department to create alternate traffic patterns for when we are working outside. In addition, we can schedule outside work so that it gets done outside of rush hour, so around 10-3. The next external risk are pests such as rodents, birds, or bugs. Pests can enter the building when there are openings to the outside. They can cause an unhygienic environment and rodents might chew through wires increasing risk of electrical fire. The best way to prepare for pests is to patch up any holes as soon as they are found before and during construction. An exterminator can also be hired to help get manage them. The next risk has to do with public opinion of the project, specifically from historical preservation societies. The Worcester Aud was built to honor WWI soldiers and there are several historical features such as the mural and pipe organ that should be preserved. If we do not honor the building’s historical meaning, we could face backlash from the public and preservation societies. This could cause construction to be stopped or we could receive fines, so it is important that we respect the heritage of the building. The best way to mitigate this risk is to include stakeholders like preservation societies in the design phase of the project. This way we can get their input and approval for the renovations before construction starts, avoiding any increases to time or budget. The last risk we might face with this project is an economic recession. Economic recessions can lead to increases in material costs and decreases in property selling prices. We can mitigate this risk by buying materials when they are cheapest and putting protocols into place such as buying a certain material immediately if the price increases from our estimate by a certain amount. This way we can make sure we stay on budget and make a profit from the project.

## Slide 14: $94,002,550
Renovation Cost

## Slide 15: Budget
Other Allowances
15.4%
Design & Engineering
5.3%
Exterior Improvement
2.3%
Demolition
9.4%
General Requirements
18.3%
Indoor Renovation
49.3%
Notes: 17,221,000 General Requirements
8,850,000 Demolition (demolition basement, 1st and 2nd floor, old elevator and restroom…)
46,386,550 Indoor Renovation (material, elevator, toilet, communication cable, HVAC, security system...)
2,120,000 Exterior Improvements (exterior and earth work...)
4,995,000 Design (Architecture and engineering design fee)
14,430,000 Other Allowances (Insurance, Contingencies)
Total 94,002,550
The total budget of our project is 94 million, and we divide the project into six parts. general requirements, demolition, design, indoor renovation, outdoor upgrade, and some other expenses.
Among them, the largest part is indoor renovation, which accounts for nearly half of the total investment. Indoor renovation, including material, elevator, toilet, communication cable, HVAC, security system
As we are renovating the memorial hall, dismantling the existing facilities is the first step. This part accounts for 9.4% of the total investment
In addition, we have to upgrade the appearance to make it a landmark building in Worcester. But in terms of investment, this part only accounts for 2.3% of the total investment.

## Slide 16: Work Breakdown Structure Project Planning Basis Facility Consolidation Facility Development
Management and Documentation
Demolition and Revitalization Construction
Transition Construction and Leasing of Marketplace
Notes: With our expenses in mind we organized our plan into three overarching categories.. Our Project Planning Basis will incorporate all members of the project management team and stakeholder representatives, this category contains workflow requiring the completion of documentation, change control board, project scope, project control processes, and reporting structures to be completed. It will also include representatives from organizations of interest such as the Architectural Heritage foundation and the Worcester Redevelopment Authority. The remaining construction work of our project divides our work into two separate categories focussing on two respective teams, construction within facility consolidation will include demolition teams and finishing teams selected for the express purpose of delicacy in removing and revitalizing the existing memorial site while removing other aspects such as the theater cleaning the basement and redeveloping the third floor balcony. The Development category in contrast involves construction teams adding new services such as ethernet and wifi as well as some rewiring of the electricity for the marketplace stalls and restaurant.

## Slide 17: Timeline 10/20-1/21 6/22-3/23 1/21-6/22 3/23
Project Team Hired & Documentation Completed
Transition Construction Conducted
Primary Construction Conducted
Project Completion
1
3
2
4
Notes: Given the allocation of the work we are doing, the fact that the project will primarily take place within Lincoln Square within the institution district, and that the facility in question is a historic memorial, we have delegated our project timeline to complete with a two and a half year margin. Our absolute deadline given the expected october launch will be in March 2023, after the severity of the New England winter normally ends and New Englanders begin returning to outdoor activities. Within the first 3 months the hiring, contracts, and archiving documentation for the project will be completed allowing for our first construction team to focus on the initial demolition and revitalization. By June the following year the modernization and redevelopment of the facility will begin and should we finish accordingly our projected completion will occur the following March at the latest including any documentation when opening the facility to the public and permitting the flow of income. To do this however in our designated timeline we seek to designate various members with specific responsibilities.

## Slide 18: Responsibilities Project Management Team Construction Team Design Team Sponsor & Stakeholder
Overseeing the project
Building the design
Designing the layout
Making key business decisions
Notes: These are the teams that will mainly be needed for the project and we will also hire consultants and contractors for specific tasks as needed, such as financial budgeting and providing construction equipment.
We have the project management team that is mainly responsible for overseeing the project. They will coordinate with the city council, make sure budget requirements are met, make sure the building is being constructed as per plan, and overall ensure things are running smoothly.
The design team will envision and create the blueprints of the building and the construction team will execute the design.
The sponsor and stakeholder will be able to make key business decisions throughout the project in order to better meet our goals.
In the project schedule, many of the tasks can be done simultaneously so we have a good amount of slack time.

## Slide 19: Levels of Effort
 | Effort Levels
Project Management Team | High
Design Team | Medium
Construction Team | Medium
Sponsor & Stakeholder | Low
Notes: The highest amount of effort level needed is from the project management team because they need to oversee the project. They will need to be present throughout the entire project.
The rest of the team members are needed for specific tasks in different areas of the project and not necessarily for the entire project. For example, the design team will need to envision and create the building design in the earlier phase of the project. In the next phase, the construction team will execute and build the design.
Overall a medium effort is needed from those teams and a low effort from the sponsor and stakeholder, mainly because the foundation and building is already in place so a lot of the work in that regards has been done. Our main purpose is to renovate the building in a way that retains the memorial look and feel while serving an enjoyable purpose for those that seek to visit the building.

## Slide 20: — David Sciarra
“This is really about community revitalization of urban areas and making our cities economically competitive, better places to live”
Notes: Conclusion Slide: David Sciarra, a practicing civil rights lawyer who has fought for socio-economic rights since 1978, once said “This is really about community revitalization for urban areas and making our cities economically competitive, better places to live.” We aim to assist the city of Worcester by making the Worcester Memorial Auditorium a hub for entrepreneurs and continue to attain the attention of college students within the area. Taking on this project would be a rewarding opportunity for vendors as the Memorial would be easily accessible for many residents living nearby and even for those taking their vehicles as the highway exit is less than a two minute drive away. The economic impact this project will have on the community of Worcester is powerful and it is within your power to take on this opportunity.

## Slide 21: Thank you for listening!
Do you have any questions?

## Slide 22: References
Gido, J., Clements, J. P., & Baker, R. (2018). Successful project management. Cengage
Learning.
Project Management Institute, Inc. (2017). A guide to the project management body of
knowledge (Pmbok guide).
Project Management Institute. (2017). Agile practice guide.